## Transformation Plan Blank
Value Stream Transformation Plan
Value Stream |  |  |  |  | Plan Review Dates
Executive Sponsor
Value Stream Champion
Value Stream Mapping Facilitator
Date Created
Priority | Problem or Proposed Countermeasure | Notes | Exec. Method * | Owner | Planned Timeline for Execution | [11 empty] | Status
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
0% | bar: Planned Timeline for Execution 1
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
Agreement
Executive Sponsor |  |  |  |  | Planned Timeline for Execution 1: Value Stream Mapping Facilitator
Signature: |  |  |  |  | Planned Timeline for Execution 1: Signature:
Date: |  |  |  |  | Planned Timeline for Execution 1: Date:
* Execution Method = JDI (Just-do-it), KE (Kaizen Event), or Proj (Project) |  |  |  |  | Planned Timeline for Execution 1: v18; Planned Timeline for Execution 7: © 2014 The Karen Martin Group, Inc.

## Transformation Plan Example
Value Stream Transformation Plan
Value Stream |  | Outpatient Imaging |  |  |  | Scheduled Review Dates
Executive Sponsor |  | Allen Ward |  |  |  | 2013-11-01
Value Stream Champion |  | Paul Scanner |  |  |  | 2013-11-21
Value Stream Mapping Facilitator |  | Dave Parks |  |  |  | 2013-12-13
Date Created |  | 2012-10-18 |  |  |  | 2014-01-10
FS VSM Block # | Measurable Target | Proposed Countermeasure |  | Exec. Method* | Owner | Planned Timeline for Execution | [11 empty] | Status
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
2 | Improve quality of referral to 85% | Implement standard work for referral process |  | KE | Sean Michaels | [12 empty] | 100%
3,4 | Reduce lead time between scheduling and preregistration step to 45 minutes | Cross-train and co-locate work teams |  | PROJ | Dianne Marie | [12 empty] | 75%
4 | Only one check in per patient | Collect copays in Imaging |  | KE | Ryan Austin | [12 empty] | 50% | bar: Planned Timeline for Execution 5
4 | Reduce wait time in waiting area by 50% | Balance work / level demand |  | KE | Dianne Marie | [12 empty] | 50%
6 | Eliminate 6 hour lead time associated with transcription step | Implement voice recognition technology |  | PROJ | Dave Gerald | [12 empty] | 50%
7 | Eliminate redundant data entry | Auto populate between PACS and Meditech |  | PROJ | Dave Gerald | [12 empty] | 25%
5 | Visually managed inventory; no outages or expired items | 5S CT supplies area; implement kanban |  | KE | Michael O'Shea | [12 empty] | 100%
6 | Reduce imaging LT to one hour | Assign value-stream specific radiologists |  | PROJ | Martha Allen | [12 empty] | 25%
8 | Reduce report delivery LT to 30 minutes | Increase % of physicians receiving electronic delivery |  | PROJ | Martha Allen | [12 empty] | 0% | bar: Planned Timeline for Execution 1 to Planned Timeline for Execution 3; Planned Timeline for Execution 7 to Planned Timeline for Execution 9
7 | Reduce LT at image review to 1 day | Visual metrics and indicators |  | JDI | Dave Gerald | [12 empty] | 100%
Agreement
Executive Sponsor |  |  | Value Stream Champion |  |  | Planned Timeline for Execution 1: Value Stream Mapping Facilitator
Signature: |  |  | Signature: |  |  | Planned Timeline for Execution 1: Signature:
Date: |  |  | Date: |  |  | Planned Timeline for Execution 1: Date:
* Execution Method = JDI (Just-do-it), KE (Kaizen Event), or Proj (Project) | [5 empty] | Planned Timeline for Execution 1: v18; Planned Timeline for Execution 8: © 2014 The Karen Martin Group, Inc.

## More Info
Order Now!
Karen Martin, President The Karen Martin Group, Inc. 858.677.6799
www.ksmartin.com